## Test Plan
Click here to see Full Test Plan for WALMART

## TestScenarios
Project Name | Walmart
Reference Document | FRS
Created By | Tasfia Zaima
Creation Date | 25-12-2024
Approval Date | 2025-02-01
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Validate the URL in different browsers. | P0 | 1
TS_002 |  | Validate the "Sign Up" functionality | P1 | 22
TS_003 |  | Validate the working of the "Sign In" functionality. | P1 | 13
TS_004 |  | Validate the working of "Logout" functionality. | P2 | 6
TS_005 |  | Validate the working of " Forget Password" functionality. | P1 | 4
TS_006 |  | Validate the working of "Header" functionality. | P4 | 4
TS_007 |  | Validate the working of "Footer" functionality. | P4 | 4
TS_008 |  | Validate the working of "Body Section" functionality. | P5 | 4
TS_009 |  | Validate the working of "Search Bar" functionality. | P5 | 2

## TestCase
Product Name |  | Walmart | TC Start Date | 25/12/2024 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account,User Management,Homepage | TC End Date | 2025-02-01 | TC Execution End Date | - - |  |  |  |  | PASS | 54
Epic |  |  | Test Case Developed By | Tasfia Zaima | Browser (tested) | Yes |  |  |  |  | FAIL | 6
Developer Name (TL) |  |  | Test Case Reviewed By | X | Performance (tested) | No |  |  |  |  | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 60
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checking if the URL site is able to run in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers- Chrome, Microsoft Edge, Brave, Mozilla Firefox | 1. Go to different browsers. 2. Search 'Walmart'. 3. Go to the website. |  |  | Passed
2 | User Management | Usability Testing | Sign Up | Check for spelling errors in error messages | No spelling mistakes | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Check for grammatical errors in confirmation messages | Messages are grammatically correct | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Verify placeholder text in input fields is correct | Should not have any typos | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Check spelling and grammar in labels, buttons and links | Should have properly formatted text | Found as per expectation. |  |  |  |  | Passed
|  | Functional Testing |  | Checking Sign up with valid details | Account is created successfully | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Sign up with an already registered email | Error message: "Email already in use" | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Sign up with an invalid email format | Error message: "Please Enter a valid email address" | Not Found as per expectation | ^^^^^_@gmail.com | 1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Continue" | Error: Invalid Email |  | Failed
|  |  |  | Sign up with a weak password | Error message: "Your password must include the following: 8–100 characters Upper & lowercase letters At least one number or special character" | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Sign up without filling required fields | Validation errors are displayed | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Sign up with mismatched passwords | Error message: "Your password must include the following: 8–100 characters Upper & lowercase letters At least one number or special character" | Found as per expectation. |  |  |  |  | Passed
|  |  |  | Sign up with phone numbers less than 10 digits | Error message:"Please enter a valid 10-digit phone number." | Found as per expectation |  |  |  |  | Passed
|  |  |  | Sign up with special characters in the username | Error message: "Please Enter a valid First or Last name" | Found as per expectation |  |  |  |  | Passed
|  |  |  | Sign up with an existing username | Error message: "Username already taken" | Found as per expectation |  |  |  |  | Passed
|  |  |  | Verify is there is an option for Gender | Should show an option | No option found as per expectation |  | 1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. Search all the fields for Gender option | Error: no gender option |  | Failed
|  |  |  | Verify if there is enough security through CAPTCHA | Should have Captcha | No option found as per expectation |  | 1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. See if there is any option for Captcha | Error: No security option like Captcha |  | Failed
|  |  |  | User session is maintained after login | User is not logged out unexpectedly | Found as per expectation |  |  |  |  | Passed
|  | UI Testing |  | Page layout is consistent across all authentication pages | No broken layouts | Found as per expectation |  |  |  |  | Passed
|  |  |  | Fonts, colors, and button styles match design guidelines | Consistent UI | Found as per expectation |  |  |  |  | Passed
|  |  |  | Fields are properly aligned and spaced | No UI distortion | Found as per expectation |  |  |  |  | Passed
|  |  |  | Error messages appear near the respective fields | Clear feedback location | Found as per expectation |  |  |  |  | Passed
|  |  |  | Login and sign-up forms are centered properly | No misalignment | Found as per expectation |  |  |  |  | Passed
|  |  |  | Mobile responsiveness works correctly | Layout adapts to different screens | Found as per expectation |  |  |  |  | Passed
6 |  | Functional Testing | Sign In | Sign in with valid credentials | User is logged in successfully | Found as per expectation |  |  |  |  | Passed
|  |  |  | Sign in with incorrect password | Error message: "Invalid password" | Found as per expectation |  |  |  |  | Passed
|  |  |  | Sign in with an unregistered email | Error message: "Email not found" | Found as per expectation |  |  |  |  | Passed
|  |  |  | Sign in with empty fields | Validation errors are displayed | Found as per expectation |  |  |  |  | Passed
|  | Usability Testing |  | Ensure error messages are user-friendly and clear | User understands the issue | Found as per expectation |  |  |  |  | Passed
|  |  |  | Check if the password field supports copy-paste (not allowed) | Works as per security policy | Not Found as per expectation |  |  | Copy Paste Password: No error |  | Failed
|  |  |  | Validate "Remember Me" functionality | User stays logged in after closing/reopening browser | Found as per expectation |  |  |  |  | Passed
|  |  |  | Enter wrong credentials multiple times | Account lockout mechanism implemented | No account lockout mechanism implemented |  |  |  |  | Failed
|  |  |  | Ensure the "Forgot Password" link is easy to locate | Users can quickly recover their password | Found as per expectation |  |  |  |  | Passed
|  | UI Testing |  | Verify the login form alignment and spacing | Properly structured form | Found as per expectation |  |  |  |  | Passed
|  |  |  | Check if the login button is clickable and visible | No UI issues | Found as per expectation |  |  |  |  | Passed
|  |  |  | Ensure password masking (bullets instead of characters) | Secure entry | Found as per expectation |  |  |  |  | Passed
7 |  |  |  | Validate that error messages appear near relevant fields | Clear feedback location | Found as per expectation |  |  |  |  | Passed
|  | UI Testing | Log Out | Ensure logout confirmation message appears properly | Message is correctly formatted | Found as per expectation |  |  |  |  | Passed
|  |  |  | Validate smooth transition when logging out | No page distortion or UI glitches | Found as per expectation |  |  |  |  | Passed
|  | Functional Testing |  | Click the logout button | User is logged out and redirected to the login page | Found as per expectation |  |  |  |  | Passed
|  |  |  | Try to access a restricted page after logout | User is redirected to the login page | Found as per expectation |  |  |  |  | Passed
|  | Usability Testing |  | Ensure the logout button is easily visible | Users can quickly find the option | Found as per expectation |  |  |  |  | Passed
|  |  |  | Provide a confirmation message after logout | Users are informed of successful logout | Found as per expectation |  |  |  |  | Passed
8 |  |  | Forget Password | Request password reset with a registered email | Password reset email is sent successfully | Found as per expectation |  |  |  |  | Passed
|  |  |  | Request password reset with an unregistered email | Error message: "Email not found" | Found as per expectation |  |  |  |  | Passed
9 |  |  |  | Reset password with a weak password | Error message: "Password must meet security criteria" | Found as per expectation |  |  |  |  | Passed
|  |  |  | Ensure reset link expires after a certain period | Expired link displays an appropriate message | Found as per expectation |  |  |  |  | Passed
28 | Homepage |  | Header | Click on the logo to navigate to the homepage | User is redirected to the homepage | Found as per expectation |  |  |  |  | Passed
|  |  |  | Verify if the header remains fixed while scrolling | Header stays visible at the top | Found as per expectation |  |  |  |  | Passed
|  |  |  | Check if navigation menu links work correctly | Links open the correct pages | Found as per expectation |  |  |  |  | Passed
29 |  |  |  | Ensure responsiveness on mobile devices | Menu adjusts properly without overlapping | Found as per expectation |  |  |  |  | Passed
30 |  |  | Footer | Click on footer links | Correct pages open in a new tab (if applicable) | Found as per expectation |  |  |  |  | Passed
|  |  |  | Verify social media icons open the correct pages | Redirects to official social media pages | Found as per expectation |  |  |  |  | Passed
|  |  |  | Check if the footer remains at the bottom on all pages | Footer stays fixed and does not overlap content | Found as per expectation |  |  |  |  | Passed
31 |  |  |  | Test responsiveness on different screen sizes | Footer content remains properly aligned | Found as per expectation |  |  |  |  | Passed
32 |  |  | Body Section | Verify that images load properly | All images appear correctly without broken links | Found as per expectation |  |  |  |  | Passed
|  |  |  | Test text alignment and formatting | Text is well-spaced, aligned, and readable | Found as per expectation |  |  |  |  | Passed
|  |  |  | Check interactive elements (buttons, forms) | Buttons and forms function as expected | Found as per expectation |  |  |  |  | Passed
33 |  |  |  | Scroll through the content to ensure smooth loading | Content loads dynamically without lag | Found as per expectation |  |  |  |  | Passed
|  |  | Search Bar | Checks if it takes in special character in search | Should show error messages | Not as per expectation |  |  | error1 |  | Failed
34 |  |  |  | Enter a valid search term and check results | Relevant search results appear | Found as per expectation |  |  |  |  | Passed
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59 |  |  | Account Login
60
61
62 |  |  | Account Login
63
64
65
66
67
68
69
70
71
72
73
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Walmart
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Sign Up, Sign In, Log out, Forget Password, Header, Footer, Search Bar, Body Section
Test Case Version | 1 |  |  |  |  | 54 | PASS
Written By | Tasfia Zaima |  |  |  |  | 6 | FAIL
Executed By | Tasfia Zaima |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | X |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 54 | 6 | 0 | 0 | 60
Grand Total | 54 | 6 | 0 | 0 | 60
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting | Bug Reporting | Bug Reporting
# SL 01 | # SL 02 | # SL 03
Issue:Sign up with an invalid email format | Issue:Verify is there is an option for Gender | Issue:Verify if there is enough security through CAPTCHA
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Continue" | 1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. Search all the fields for Gender option | 1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. See if there is any option for Captcha
Env: Production | Env: Production | Env: Production
Module: Sign Up | Module: Sign Up | Module: Sign Up
Severity: P1 | Severity: P4 | Severity: P5
Error: Invalid Email | Screenshot_3.png | Screenshot_3.png
Responsible QA: Tasfia Zaima | Responsible QA: Tasfia Zaima | Responsible QA: Tasfia Zaima
Bug Reporting | Bug Reporting | Bug Reporting
# SL 04 | # SL 05 | # SL 06
Issue: Check if the password field supports copy-paste (not allowed) | Issue: Enter wrong credentials multiple times | Issue: Checks if it takes in special character in search
Reproducing Steps: | Reproducing Steps: | Reproducing Steps:
1. Goto the URL walmart.com 2. Click on the " Sign In" button at the right corner 3. Fill the password fieldby copy pasting password from elsewhere 4. Click ''Continue" | 1. Goto the URL walmart.com 2. Click on the " Sign In or Create Account" button at the right corner 3. Fill all the fields with invalid credentials many times 4. Click ''Continue" | 1. Goto the URL walmart.com 2. Click on the " Search" button at the top. 3. Fill the search field with special characters 4. Click Search icon
Env: Production | Env: Production | Env: Production
Module: Sign In | Module: Sign In | Module: Search Bar
Severity: P4 | Severity: P4 | Severity: P4
Responsible QA: Tasfia Zaima | Responsible QA: Tasfia Zaima | Responsible QA: Tasfia Zaima

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (60/60)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (54/60)*100 = 90%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (6/60)*100 = 10%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A